## Sheet1
Task |  | Assign to | Done/not | Week4 |  |  |  |  | Week5 |  |  |  |  | Week6 |  |  |  |  | Week7 |  |  |  |  | Week8 |  |  |  |  | Alpha | Week9
|  |  |  | 03-Jun | 04-Jun | 05-Jun | 06-Jun | 07-Jun | 10-Jun | 11-Jun | 12-Jun | 13-Jun | 14-Jun | 17-Jun | 18-Jun | 19-Jun | 20-Jun | 21-Jun | 24-Jun | 25-Jun | 26-Jun | 27-Jun | 28-Jun | 01-Jul | 02-Jul | 03-Jul | 04-Jul | 05-Jul |  | 09-Jul | 10-Jul | 11-Jul | 12-Jul
Design
GDD | Boss Skill Design | Designers | [5 empty] | Done
GDD | Character Basic action Design | Designers
Visio | Level Design | Designers | [6 empty] | Done
Visio | Level Set up | Designers
Prototype | Value settings | Designers
Prototype | Value adujstmetn | Designers
Prototype | AI research | Designers
Prototype | AI system | Designers
Prototype | Design Optimize | Designers
Programming
Function | Character action Function | John | [8 empty] | Done Advanced
Animation | Chracter animation | Dean,Leon | [9 empty] | Done
UI | Prototype UI | Dean,Leon
Function | Boss action Function | John
Animation | Boss animation | Dean,Leon
System | Combat system | John
System | AI system | John
UI | Prototype UI Refine | Leon
Art
Concept | Scene Concept | Kiki | [7 empty] | Done
Scene | Background enviroment | Kiki
Action Design | Chracter Skill Design | Eunise | [6 empty] | Done Advanced
Animation | Chracter Animation Making | Eunise
Concept | Boss Concept | Kiki
Action Design | Boss Skill Design | Eunise
Animation | Boss Animation Making | Eunise
SFX | The frame of special effects | Kiki
SFX | Particle effect | Kiki