## WBS
Department | Outline(Responsible) | Period | Work breakdown structure | Plan Start Date | Plan Duration(Days) no weekend | DateValue
Design | Action Design(All Designer) | start | Boss Skill Design | 2019-06-03 | 4 | 43619
|  | doing | Character basic action Design | 2019-06-07 | 1 | 43623
| Basic action data(Niko) | backlog | Data settings | 2019-06-11 | 1 | 43627
|  | backlog | Data adjustment | 2019-06-12 | 1 | 43628
| AI(Hugo) | backlog | AI reasearch | 2019-06-10 | 3 | 43626
|  | backlog | AI system | 2019-06-13 | 2 | 43629
| Battle system data(Westrice) | backlog | Data settings | 2019-06-19 | 2 | 43635
|  | backlog | Data adjustment | 2019-06-21 | 1 | 43636
| Animation(All Designers) | doing | Animation making | 2019-06-10 | 15 | 43626
Programming | Combat system(All coders) | backlog | Character function | 2019-06-03 | 7 | 43619
|  | backlog | Boss function | 2019-06-12 | 5 | 43628
| AI system(Jhon) | backlog | AI function | 2019-06-15 | 5 | 43631
Art | Boss&Character(Artists) | backlog | Boss concept(Kiki) | 2019-06-03 | 5 | 43619
|  | backlog | Boss Skill Design(Eunise) | 2019-06-03 | 9 | 43619
|  | refine | Character concept(Kiki) | 2019-06-10 | 3 | 43626
|  | doing | Character skill Design(Eunise) | 2019-06-14 | 8 | 43629
| Scene(Kiki) | backlog | Scene concept art | 2019-06-13 | 5 | 43629
|  | backlog | scene elements set | 2019-06-19 | 2 | 43635
| SFX(Kiki) | backlog | The frame of special effects | 2019-06-21 | 4 | 43637
|  | backlog | Particle effects | 2019-06-27 | 5 | 43643